## Introduction
The purpose of this spread sheet is to provide a summary of SAE J1699-5 Task Force work items and a list of pending software changes.
The J1699-5 applciation can be found at https://portal.autosinnovate.org/obd-certification-public-access/
The SAE J1699-5 Task Force Chairman is Mark Zackos. Mark's e-mail address is mark@dgtech.com
Software questions/issues can be directed to Kevin Stofflet at kstofflet@engenius.com.
Last Value
J1699-3 Issue Numbers that have also been fixed in J1699-5 | 3-xxxx
J1699-5 Issue Numbers | 5-10047

## J1699-5 Task Force Work Items
Type | Issue Number | Description | Requestor | Open Date | Accept Date | Priority/ Release | Close Date | Status
Items Pending Review
Add Feature | 5-10047 | Change INF $F86D-76 verification to fail if Lifetime data is zero. | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | T
Add Feature | 5-10046 | Change INF $F867-6C verification to fail if Stored data is zero. | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | T
Add Feature | 5-10045 | Change INF $F861-66 verification to fail if Active data is not zero after clear codes command. | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | T
Add Feature | 5-10044 | Change INF $F851-5B verification to fail if Stored and Lifetime counters are zero. | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | T
Add Feature | 5-10043 | Change INF $F848-50 verification to fail if Stored and Lifetime counters are zero for PHEV and warn if Active and Lifetime counters are both zero for PHEV. | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | T
Add Feature | 5-10042 | Change INF $F847 verification to fail if Total and Idle PSA time Lifetime counters are zero for P/HEV and warn if Urban PSA Active and Lifetime counters are zero for P/HEV. | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | T
Add Feature | 5-10041 | Change INF $F846 verification to fail if Idle run time lifetime counter are zero and warn if Engine FC and Idle FC, PKE, and Urban Speed Run counters are zero. | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | T
Add Feature | 5-10040 | Change INF $F845 verification to fail if ERT and EOE lifetime counters are zero for CONV and S/S or warn if P/HEV, and warn if DT and FC lifetime counter are zero. | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | T
Add Feature | 5-10039 | Change INF $F842 verification to fail if Idle Active counters (except Idle FC, see 3-1067) are zero and warn if Engine FC, Idle FC, Urban Speed Run, and PKE counters are zero. | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | T
Add Feature | 5-10038 | Change INF $F841 verification to fail if ERT and EOE Active counters are zero for CONV and S/S or warn if P/HEV, and warn if DT and FC Active counter are zero. | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | T
Add Feature | 5-10037 | Change INF $F81D-1F,21-2A evaluation to warn if Recent and Lifetime values are equal or zero and warn if it is supported but all timers are "not available". | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | T
Add Feature | 5-10036 | Change INF $F81A-1C evaluation to warn if Recent and Lifetime values are equal or zero for PHEV. | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | T
Add Feature | 5-10035 | Change INF $F819 evaluation to fail if Recent and Lifetime values are equal or zero for Total and Idle PSA and warn if Recent and Lifetime values are zero or Equal for City PSA. | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | T
Add Feature | 5-10034 | Change INF $F818 evaluation to fail if Recent and Lifetime values are equal or zero for CONV and S/S or warn for HEV and PHEV. | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | T
Add Feature | 5-10033 | Change INF $F817 evaluation to warn if Recent and Lifetime DT values are zero OR equal, warn if Recent and Lifetime FC values are zero for HEV or PHEV, fail if Recent and Lifetime FC values are equal for CONV and S/S, and fail if Fuel Consumed Bytes not supported for EOBD. | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | T
Add Feature | 5-10032 | Added evaluation for PIDs $F4CF,D3,and D7. | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | T
Add Feature | 5-10031 | Added required support evaluate for INF $F883 and $F884. | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | T
Add Feature | 5-10030 | Added function to evaluate INF $F82A. | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | T
Bug Fix | 5-10029 | Fix formatting of printing of values in PID $F4C9 and $F4CB. | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Fixed in V03.05.00, dated 4/25/2024. | T
Bug Fix | 5-10028 | Fix PID display for $F505 (it used to mistakely show $F504). | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Fixed in V03.05.00, dated 4/25/2024. | T
Bug Fix | 5-10027 | Fix MDDC check for PID $F4A2 (was incorrectly compared to gstUserInput.eComplianceType, now compared to gstUserInput.eVehicleType). | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Fixed in V03.05.00, dated 4/25/2024. | T
Bug Fix | 5-10026 | Fix the misspelling in RequestGrouPIDSupportData to RequestGroupPIDSupportData (found while working on 5-10017). | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Fixed in V03.05.00, dated 4/25/2024. | T
Bug Fix | 5-10025 | Comment out MID tests (and VerifyVehicleState tests when the rest of the test section is not performed). | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Fixed in V03.05.00, dated 4/25/2024. | T
Bug Fix | 5-10024 | Clean up defunct, commented-out code and change Physically/Functionally addressed coding for new standard. | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Fixed in V03.05.00, dated 4/25/2024. | T
Bug Fix | 5-10023 | Add size checks for PID $F4A7,A8,AA,AC-B1,C3,C7,C9,CB,CF,D3,D7. | J1699-5 V3.5 | 2024-04-25 |  | 03.05.00 | 2024-04-25 | Fixed in V03.05.00, dated 4/25/2024. | T
Add Feature | 5-10022 | Add ZEV Validation Tests. | J1699-5 | 2024-03-25 |  |  | NEED DOC. UPDATE |  | T
Add Feature | 5-10021 | Support SMAD (INF $92-$93) in Mfg. Specific Drive Cycle. | J1699-5 V3.3 | 2024-03-25 |  |  |  |  | T
Open Items
Add Feature | 5-10020 | Allow NRC $22 (Conditions Not Correct) for SID $22 under EOBD. | shikha.rathi@volvo.com | 2024-01-24 |  |  | NEED DOC. UPDATE | 2/26/2024 - Consulting with J1979. 3/1/2024 - NRC $22 (Conditions Not Correct) is allowed for SID $22 in US, but is allowed in EU. Implementataion must wait until after US OBD is fully implemented. | T
Add Feature | 5-10019 | Don't fail vehicles that do not support cylinders 9-16 and do not support SID $22 $F503 and $F505. Don't fail if MISx_CUR_DCY is non-zero. | J1699-5 V3.3 | 2024-01-24 | 2024-03-01 | 03.05.00 | 4/25/2024 NEED DOC. UPDATE | 12/8/2023 - TF to review. 3/1/2024 - Don't fail if DID is not supported. Don't fail if MISx_CUR_DCY is non-zero (per V3.6 J1699-5). Added in V03.05.00, dated 4/25/2024. | T
Add Feature | 5-10018 | Test 5.5 / Test 5.13 F6xx Validation; Check for supporting what you say you support and verify response size… no test result validation. | J1699-5 V3.3 | 2024-01-24 | 2024-03-01 |  | NEED DOC. UPDATE | UDS does not repeat Monitor ID in Test Results, so size will be different than in J1699-3. | T
Bug Fix | 5-10014 | Test 5.6 is failing all ECUs if they do not support EGS, CV, EGR, CSER. | shikha.rathi@volvo.com | 2023-10-11 | 2023-12-08 | 02.06.01 | 11/8/2023 NEED DOC. UPDATE | Fixed in V02.06.01, dated 11/8/2023 | TI
Investigate | 5-10013 | Reverse Order test fails on V02.06.00, but works on V02.03.00. | shikha.rathi@volvo.com | 2023-09-27 | 2023-09-29 |  |  |  | T
Add Feature | 5-10011 | Test 5.11 of J1699-5, FreezeFrame data shall be requested SERVICE $19 SUBSERVICE $04. The SW actually requests SERVICE $19 SUBSERVICE $03 instead. | Hans.Joerg.Brinksmeyer@Volkswagen.de | 2023-09-06 | 2023-09-29 | 02.06.01 | 11/8/2023 NEED DOC. UPDATE | 9/29/2023 - TF to remove test. Fixed in V02.06.01, dated 11/8/2023 | TI
Add Feature | 5-10001 | Add support for ETHERNET_NDIS. | Task Force / V2.5 Document | 2023-05-18 | 2023-07-14 |  |  |  | PTI
Add Feature | 3-1080 | Test 5.17 fails with "Supports INF $7A (Must not support INF higher than $78)". Need to support more INFs. | theikkin@volvocars.com | 2024-02-12 |  | 03.05.00 | 4/25/2024 NEED DOC. UPDATE | Added in V03.05.00, dated 4/25/2024. | T
Add Feature | 3-1079 | Test 5.17 and Test 9.24 must also check INFs $16-$29 are checked for max. value or "not available". | extern.oliver.schiemann@volkswagen.de | 2024-02-02 | 2024-03-01 | 03.05.00 | 4/25/2024 NEED DOC. UPDATE | Added in V03.05.00, dated 4/25/2024. | T
Add Feature | 3-1077 | Q03 Prompt needs to accept >2025 MY. | extern.oliver.schiemann@volkswagen.de | 2024-02-02 | 2024-03-01 | 03.05.00 | 4/25/2024 NEED DOC. UPDATE | Added in V03.05.00, dated 4/25/2024. | PTI
Add Feature | 3-1075 | SID $09 INF $47 should only apply to PHEV/EV. | john.v.bowman@gm.com | 2024-01-29 | 2024-03-01 | 03.05.00 | 4/25/2024 NEED DOC. UPDATE | Added in V03.05.00, dated 4/25/2024. | PTI
Add Feature | 3-1072 | Test 5.17, INFs $52-$5B should change from a FAILURE to a WARNING. | Task Force | 2023-12-09 | 2024-03-01 | 03.05.00 | 4/25/2024 NEED DOC. UPDATE | Added in V03.05.00, dated 4/25/2024. | PTI
Add Feature | 3-1071 | Test 5.17, INF $51 applies to S/S only. | Task Force | 2023-12-09 | 2024-03-01 | 03.05.00 | 4/25/2024 NEED DOC. UPDATE | Added in V03.05.00, dated 4/25/2024. | PTI
Add Feature | 3-1070 | Test 5.17, INFs $48, $49, and $50 apply to PHEV only. | Task Force | 2023-12-09 | 2024-03-01 | 03.05.00 | 4/25/2024 NEED DOC. UPDATE | Added in V03.05.00, dated 4/25/2024. | PTI
Add Feature | 3-1069 | Test 5.17.85, Evaluation criteria is changing to != 0 | Task Force | 2023-12-09 | 2024-03-01 | 03.05.00 | 4/25/2024 NEED DOC. UPDATE | Added in V03.05.00, dated 4/25/2024. | PTI
Add Feature | 3-1067 | Test 5.17, Failure: ECU 18DAF110 INF $42 IEFC-A must return a value of greater than 1. The problem begins when the Clear DTC command included in Test 5.9 resets the active bin information (INF $42 - Engine Idle Fuel Consumption (Active) = 0.0L). In the attached log file, this Clear DTC command occurs approximately 260s prior to INF $42 being requested. Due to the fact, that INF $42 is measured in 0.5L increments and it is not realistic to consume 0.5L of fuel that quickly, a value of 0.0L is reported in Test5.17 and the failure is registered. | jacob.rauser@volvo.com | 2023-11-30 | 2023-12-08 | 03.05.00 | 4/25/2024 NEED DOC. UPDATE | 12/8/2023 - TF agrees to remove value check. Added in V03.05.00, dated 4/25/2024. | PTI
Bug Fix | 3-1056 | Test 5.9, Not all ECUs respond to SID $04, but no error is flagged. | Hans.Joerg.Brinksmeyer@Volkswagen.de | 2023-06-07 | 2023-07-14 |  | NEED DOC. UPDATE | Section 5.9.1 is clear that all OBD ECUs must respond negatively, if one does. Code is currently test only ECUs that respond. Section 5.3 is not clear on who must reply for ISO 15765 (do we want logic similar to 5.9.1). Code is currently test only ECUs that respond. | T
Add Feature | 3-1050 | There is a large time gap between request and receive. | brianp@dashlogic.com | 2023-03-23 | 2023-03-23 |  |  |  | T
Add Feature | 3-1046 | Define a new test for a group PID requests containing a known unsupported PID. | Task Force | 2023-01-13 | 2023-01-13 |  | NEED DOC. UPDATE |  | T
Add Feature | 3-1014 | Discuss support for CNG engines in J1699. | yong.yu@arb.ca.gov |  |  |  | NEED DOC. UPDATE |  | T
Bug Fix | 3-1011 | Test 9.23 seems to abort after choosing not to continue with Dynamic Tests. | brandon.baumgartner@stellantis.com |  |  |  |  | It is unclear what is going on here. | T
Bug Fix | 3-1010 | Test 9.19: 407 second gap in network activity resulting in false failure. | GyuMan.Hwang@hyundai-kefico.com |  |  |  |  | It is unclear what is going on here. 3/16/22 - This is a sumulation on a HIL, with bad data. J2534 firmware upated and will retest with appropriate data. THIS DOES NOT APPEAR TO BE A J1699-3 SOFTWARE ISSUE. | T
Add Feature | 3-1007 | Test 5.14 WARNs on SID $96 MID $81 if limits not 0, but this test in in KOER so the limits may not be 0. | john.v.bowman@gm.com |  |  |  | NEED DOC. UPDATE | 11/12/2021 - TF agreed to move this test to KOEO portion of test. | PTI
Discussion | Not Assigned | Are all UDS OBD II ECU required to respond to 22 F400 and 22 F500 as J1979-2 indicates? Do we need test cases to compare ECUs list to 22 F810? | Mark.Wine@opusivs.com | 2023-01-03 | 2023-01-13 |  |  | 1/13/2023 - Task Force will send this to the Small Group for consideration. | T
Discussion | Not Assigned | The Group PID request from J1699-3 are missing from the document. | J1699 | 2022-12-19 | 2023-01-13 |  |  | 1/13/2023 - Task Force will send this to the Small Group for consideration. | T
Items on HOLD
Closed Items
Add Feature | 5-10017 | PID Supported PIDs F4E0 and F5E0 should both have bit 0 set to 0. | J1699-5 V3.3 | 2024-01-24 | 2024-03-01 | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | PTI
Add Feature | 5-10016 | Add definitions for EnergyType and FuelType and remove EngineType and gbDiesel to match document. | Task Force / V2.6 Document | 2023-10-31 | 2023-12-08 | 02.06.01 | 2023-11-08 | Fixed in V02.06.01, dated 11/8/2023 | TI
Add Feature | 5-10015 | Change Europe and China compliance types to better match document. | Task Force / V2.6 Document | 2023-10-31 | 2023-12-08 | 02.06.01 | 2023-11-08 | Fixed in V02.06.01, dated 11/8/2023 | TI
Bug Fix | 5-10012 | Byte #4 in a Freeze Frame Response should be $FF, but J1699-5 expects $04. Test 5.14 / Test 8.3 / Test 9.3 with a false WARNING. Test 6.3 ends up in an infinite loop, based upon the same issue. | Hans.Joerg.Brinksmeyer@Volkswagen.de | 2023-09-06 | 2023-09-29 | 02.06.01 | 2023-11-08 | Fixed in V02.06.01, dated 11/8/2023 | TI
Bug Fix | 5-10010 | Test 5.10 evaluation of PID $F501 issues with engine running. | Hans.Joerg.Brinksmeyer@Volkswagen.de | 2023-09-06 | 2023-09-29 | 02.06.01 | 2023-11-08 | Fixed in V02.06.01, dated 11/8/2023 | TI
Bug Fix | 5-10009 | When testing on a light duty car, J1699-5 requires heavy duty PIDs to be present. | Hans.Joerg.Brinksmeyer@Volkswagen.de | 2023-09-06 | 2023-09-29 | 02.06.01 | 2023-11-08 | Fixed in V02.06.01, dated 11/8/2023 | TI
Bug Fix | 5-10008 | Test 5.8 ends when there is no response to PID $F40D on 29-bit, but a link monitor shows there was a response. | Hans.Joerg.Brinksmeyer@Volkswagen.de | 2023-09-06 | 2023-09-29 | 02.06.01 | 2023-11-08 | Fixed in V02.06.01, dated 11/8/2023 | TI
Bug Fix | 5-10007 | Allow subtest to continue after failure in DID-Support DID check. | kstofflet@engenius.com | 2023-08-03 | 2023-09-29 | 02.06.00 | 2023-08-07 | Fixed in V02.06.00, dated 8/7/2023. | TI
Add Feature | 5-10006 | Remove Tester Present option. | Small Group | 2023-08-03 | 2023-09-29 | 02.06.00 | 2023-08-07 | Added in V02.06.00, dated 8/7/2023. | TI
Add Feature | 5-10005 | Implement J1699-5 specified Dynamic Test (IUMPR equivalent). | Task Force / V2.6 Document | 2023-07-31 | 2023-09-29 | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | PTI
Add Feature | 5-10004 | Support the MIL Exclusion file, like J1699-3 does. | john.v.bowman@gm.com | 2023-07-14 | 2023-09-29 | 02.06.00 | 2023-08-07 | Added in V02.06.00, dated 8/7/2023. | TI
Add Feature | 5-10003 | Test 5.5, 5.6 FAILs ECUs because physical requests are being made to ECUs that indicate they do not support the parameter. |  | 2023-06-01 | 2023-07-14 | 02.06.00 | 2023-08-07 | Task Force to clarify NRCs allowed. Added in V02.06.00, dated 8/7/2023. | TI
Add Feature | 5-10002 | Test 5.8 communication seems to stop after protocol check (no further response received). |  | 2023-06-01 | 2023-07-14 | 02.06.00 | 2023-08-07 | May be related to NRC issue. Added in V02.06.00, dated 8/7/2023. | TI
Bug Fix | 5-10000 | Protocol determination uses SID $01 PID $00, but it should use SID $22 PID $F810. | Hans.Joerg.Brinksmeyer@Volkswagen.de | 2022-06-17 | 2022-07-22 | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Bug Fix | 3-1078 | Q10 Prompt needs to accept more than one digit. | Hans.Joerg.Brinksmeyer@Volkswagen.de | 2024-02-02 |  | 03.05.00 | 2024-04-25 | Fixed in V03.05.00, dated 4/25/2024. | T
Bug Fix | 3-1076 | SID $01 PID $A3 has evaluation criteria in code, but there is no requirement in the document. | Gabor.Tarnai@vitesco.com | 2024-02-02 | 2024-03-01 | 03.05.00 | 2024-04-25 | Fixed in V03.05.00, dated 4/25/2024. | T
Bug Fix | 3-1066 | Using J1699_CONFIG.INI, Test 5.17 is producing "FAILURE: INF $6 (CVN) supported by less than the expected number of ECUs ( 1 support, 1 expected)!", but it seems like it shouldn't. | topi.heikkinen@volvocars.com | 2023-10-18 | 2023-12-08 | 03.05.00 | 2024-04-25 | Fixed in V03.05.00, dated 4/25/2024. | T
Bug Fix | 3-1065 | False fail for unsupported signals in tracking INFs like $17 in EU. | Hans.Joerg.Brinksmeyer@Volkswagen.de | 2023-09-27 | 2023-09-29 | 02.06.01 | 2023-11-08 | Since EU does not require “recent” values in the INFs, an ECU may report 0xFFFF as indication of unsupported values. We already had this problem tracked as issue 290. Back in those days we had solved this very issue in Version 16.07.00. Now, in the actual version(s) it shows up again. Fixed in V02.06.01, dated 11/8/2023 | TI
Bug Fix | 3-1063 | Test 5.17 for SID $09 INF $77 should WARN for 2022-2023 and FAIL for 2024, but currently FAILs . | shikha.rathi@volvo.com | 2023-08-28 | 2023-09-29 | 02.06.01 | 2023-11-08 | Fixed in V02.06.01, dated 11/8/2023 | TI
Add Feature | 3-1062 | SID $09 INF $78 should only apply to diesel MD, MDDC, and HD. | john.v.bowman@gm.com | 2023-08-04 | 2023-09-29 | 02.06.01 | 2023-11-08 | Fixed in V02.06.01, dated 11/8/2023 | TI
Bug Fix | 3-1060 | Fix bug that would cause crash if current and previous vehicle test type did not match. | kstofflet@engenius.com | 2023-07-14 | 2023-09-29 | 02.06.00 | 2023-08-07 | Added in V02.06.00, dated 8/7/2023. | TI
Bug Fix | 3-1057 | Test 11.2, ESC key not functioning correctly, it causes test to FAIL instead of EXIT. | Hans.Joerg.Brinksmeyer@Volkswagen.de | 2023-07-13 | 2023-07-14 | 02.06.00 | 2023-08-07 | Added in V02.06.00, dated 8/7/2023. | TI
Add Feature | 3-1054 | Correct EOBD Code Clear to allow a mixed response only on Key On Engine Running. | Task Force | 2023-05-19 | 2023-05-19 | 02.06.00 | 2023-08-07 | Added in V02.06.00, dated 8/7/2023. | TI
Bug Fix | 3-1053 | Application is locking up at splash screen with Windows 11 Pro, Ver 22H2 OSbuild 22621.1702. | RobertT@NRD.NISSAN-USA.COM | 2023-05-18 | 2023-07-14 | 02.06.00 | 2023-08-07 | Fixed in V02.06.00, dated 8/7/2023. | TI
Bug Fix | 3-1052 | In Test 11.2, displays IUMPR incorrect initial counters for ECUs that are not on the 'first page'. | Peter.Crawford@kiageorgia.com | 2023-05-04 | 2023-05-19 | 02.06.00 | 2023-08-07 | Fixed in V02.06.00, dated 8/7/2023. | TI
Bug Fix | 3-1051 | In Test 11.2, do not display IUMPR info for ECUs that do not support IUMPR but do support I/M Readiness. Currently the counter names and zeros are displayed. | Peter.Crawford@kiageorgia.com | 2023-05-04 | 2023-05-19 | 02.06.00 | 2023-08-07 | Fixed in V02.06.00, dated 8/7/2023. | TI
Add Feature | 3-1049 | On partially compliant J2534 Interfaces, errors are logged when attempting to clear filters on a channel that was never opened. | brianp@dashlogic.com | 2023-03-23 | 2023-03-23 | 02.06.00 | 2023-08-07 | Added in V02.06.00, dated 8/7/2023. | TI
Add Feature | 3-1048 | SID $09 INF $77 should not have a phase in period. | Task Force | 2023-03-23 | 2023-03-23 | 02.06.00 | 2023-08-07 | Added in V02.06.00, dated 8/7/2023. | TI
Add Feature | 3-1047 | Update the wording in Test 6.1 that requests a two trip DTC. | john.v.bowman@gm.com | 2021-08-08 | 2023-03-24 | 02.06.00 | 2023-08-07 | Also change "disconnect sensor" to "induce fault" throughtout code. Added in V02.06.00, dated 8/7/2023. | TI
Bug Fix | 3-1041 | Fix display resolution loss in calculation of PID $85 and $96 from using TempData_long instead of TempData_float (display only, no evaluation of these PIDS). | kstofflet@engenius.com | 2023-02-13 | 2023-03-24 | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Bug Fix | 3-1040 | Fix display resolution loss in calculation of PID $85 and $96 from using TempData_long instead of TempData_float (display only, no evaluation of these PIDS). | kstofflet@engenius.com | 2023-02-13 | 2023-03-24 | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Bug Fix | 3-1039 | Test 5.6, PID $A1 has an incorrect data transformation. It lists NOXC12_SUP but should be NOXC12_SUP; NOXC12_SUP should be NOXC21_SUP; NOXC11_DAT_AVAIL is listed for NOXC12, NOXC21, and NOXC22; Also the data evauluation for NOXC11 and NOXC12 is comparing TempData_float instead of TempData_long. | shikha.rathi@volvo.com | 2023-02-13 | 2023-03-24 | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Add Feature | 3-1035 | Split MD and LD in the Vehicle Type prompt, including all tests that use this logic. | Task Force | 2023-01-13 | 2023-01-13 | 02.06.00 | 2023-08-07 | Added in V02.06.00, dated 8/7/2023. | TI
Add Feature | 3-1034 | Clarify wording in the phase-in WARNING for new INFs. | Task Force | 2023-01-13 | 2023-01-13 | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Add Feature | 3-1033 | Clarify wording in Q03 to indicate it is VIN Model Year. | Task Force | 2023-01-13 | 2023-01-13 | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Bug Fix | 3-1031 | Test 11.2 waiting for Bank2 to complete, when vehicle only has Bank1. | hans.joerg.brinksmeyer@volkswagen.de | 2022-12-22 | 2023-01-13 | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Bug Fix | 3-1030 | Test 9.19 and 11.2 crash with China6 selected. | hans.joerg.brinksmeyer@volkswagen.de | 2022-12-22 | 2023-01-13 | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Bug Fix | 3-1029 | Test11.2 with implausible data for initial IUMPRs | hans.joerg.brinksmeyer@volkswagen.de | 2022-12-19 | 2023-01-13 | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Bug Fix | 3-1028 | Extra space added between "*" and "T" (+000000ms RESULTS: **** Test 5.1 PASSED ****), which breaks tools. It needs to be added back. | hans.joerg.brinksmeyer@volkswagen.de | 2022-12-19 | 2023-01-13 | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Bug Fix | 3-1027 | False failure in Test 5.17 for missing INF $78. This should be for HD and MD only, not LD. | hans.joerg.brinksmeyer@volkswagen.de | 2022-12-19 | 2023-01-13 | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Bug Fix | 3-1025 | In the Dynamic Test, after logging the meta information, it starts somewhere within Test 10.3. So, Tests 10.1 and 10.2 are missing completely, the same is true for the first part of Test 10.3. | hans.joerg.brinksmeyer@volkswagen.de | 2022-12-19 | 2023-01-13 | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Bug Fix | 3-1024 | Test 5.18 incorrectly flags the response to a SID $01 PID $E0, $C0 group request as a failure if $E0 is not supported. | Jianwei_Zhong@PATAC.com.cn | 2022-11-15 |  | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Add Feature | 3-1021 | Fix confusing error message when ECU didn't respond or responded with incorrect ID to PIDSupported PID. | Bosch |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | TI
Add Feature | 3-1020 | China6 does not require all or nothing when clearing codes like OBD II does (e.g., during KOER)? | Mitchell.Olson@na.mitsubishi-motors.com |  |  | 02.03.00 | 2023-03-14 | Looks like this is not a requirement for China6; 3/11/22 TF - M. Laleman confirmed this. Fixed in V02.03.00, dated 3/14/2023. | TI
Add Feature | 3-1019 | INF $78 RPM range should be up to 5000 for all vehicles. | J1699-3 TF |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | TI
Add Feature | 3-1018 | In Test 5.17, remove the evaluation criteria for checking the Stored parameter, but leave the criteria for doing the length check in infotypes $43, $44, $67, $68, $69 and $6A. | J1699-3 TF |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | TI
Bug Fix | 3-1016 | Tests 11.5 and 11.8 have a mismatch between the Mode $01 PID $01 data actually reported by the ECU and the new “information view” onto the readiness data. | hans.joerg.brinksmeyer@volkswagen.de |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | TI
Add Feature | 3-1013 | Test 5.17 GHG INF requirements apply to all HD Vehicles. Should this also consider the type of Regulatory/Engine/Powertrain? | john.v.bowman@gm.com |  |  | 02.03.00 | 2023-03-14 | John has a table to try an identify valid combinations. 1/14/22 TF to set up small group meeting to define requirements. Fixed in V02.03.00, dated 3/14/2023. | TI
Add Feature | 3-1012 | Proposal to add a prompt for Engine Certification Year and suggestions on how it a VIN should be evaluated. | john.v.bowman@gm.com |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | TI
Bug Fix | 3-1009 | Test 5.17 request the next unsupported INFSupported INF, but there is no longer a requirement to do this. This code should be removed from the software | john.v.bowman@gm.com |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | TI
Add Feature | 3-1006 | Test 5.17 Nox BINs 2-17 compare to BIN 1 must be +-1% to allow for allow for resolution and error compounding. | john.v.bowman@gm.com |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | TI
Add Feature | 3-1005 | SID $09 INF $6D, $6E, $6F, and $70 fail if value == 0, but 0 is valid value. | john.v.bowman@gm.com |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | TI
Add Feature | 3-1004 | Test 5.17 does not support INF greater than $29. | john.v.bowman@gm.com |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | TI
Add Feature | 3-1003 | SID $09 INF $78 needs to allow Diesels to have a range of x > 0 | john.v.bowman@gm.com |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | T
Bug Fix | 3-1002 | Error if SID $09 INF $6D has a value of 0. Should test fail ONLY if Lifetime < Active; If Lifetime = Active = 0 then it should pass. | john.v.bowman@gm.com |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | T
Bug Fix | 3-1001 | Test 7.5, 8.5, and 9.5 produce errors regarding PID$C0 Group request mismatch. Test 5.18 produces errors regarding PID$C3 support | john.v.bowman@gm.com |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | T
Bug Fix | 3-1000 | Reverse order PID request is failing when ECU supports less than 6 PIDs. | KiWang.Kim@hyundai-kefico.com |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | T
Add Feature | 3-220 | The Burst Test (Test 5.20) fails due to PC factors outside of the control of the J1699-3 software (e.g., virus scanning software, Windows, etc.). The evaluation criteria should be changed to examine only the ECU response times over say 200 requests. This would eliminate the impact of PC delays because we would not be counting the number of message round-trips for a given period of time. Instead, we would only be examining the ECU response times as derived from the Pass-Thru Device message data, which would not be impacted by PC delays. | Hans.Joerg.Brinksmeyer@Volkswagen.de |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | TI
Discussion | Not Assigned | Can we get rid of the Tester Present option? | Hans.Joerg.Brinksmeyer@Volkswagen.de | 2023-06-07 | 2023-07-14 | Closed | 2023-08-07 | Removed see Issue 5-10006 | T

## J1699-5 Work Schedule
Approximate Release Date | SF # | Description | J1699-5 Status
Mid-Mar., 2023
| 3-1013 | Test 5.17 GHG INF requirements apply to all HD Vehicles. Should also consider the type of Regulatory/Engine/Powertrain. | In J1699-5
| 3-1020 | China6 does not require all or nothing when clearing codes like OBD II does (e.g., during KOER). | In J1699-5
| 3-1024 | Test 5.18 incorrectly flags the response to a SID $01 PID $E0, $C0 group request as a failure if $E0 is not supported. | In J1699-5
| 3-1025 | In the Dynamic Test, after logging the meta information, it starts somewhere within Test 10.3. So, Tests 10.1 and 10.2 are missing completely, the same is true for the first part of Test 10.3. | In J1699-5
| 3-1027 | False failure in Test 5.17 for missing INF $78. This should be for HD and MD only, not LD. | In J1699-5
| 3-1028 | Extra space added between "*" and "T" (+000000ms RESULTS: **** Test 5.1 PASSED ****), which breaks tools. It needs to be added back. | In J1699-5
| 3-1029 | Test 11.2 with implausible data for initial IUMPRs | In J1699-5
| 3-1030 | Test 9.19 and 11.2 crash with China6 selected. | In J1699-5
| 3-1031 | Test 11.2 waiting for Bank2 to complete, when vehicle only has Bank1. | In J1699-5
| 3-1033 | Clarify wording in Q03 to indicate it is VIN Model Year. | In J1699-5
| 3-1034 | Clarify wording in the phase-in WARNING for new INFs. | In J1699-5
| 3-1039 | Test 5.6, PID $A1 has an incorrect data transformation. | In J1699-5
| 3-1040 | Fix display resolution loss in calculation of PID $85 and $96. | In J1699-5
| 3-1041 | Change TEST 11.2 on-screen text from RESERVED to GPF for gasoline vehicles. | In J1699-5
| 5-10000 | Protocol determination uses SID $01 PID $00, but it should use SID $22 PID $F810. | In J1699-5
Early August, 2023
| 3-1035 | Split MD and LD in the Vehicle Type prompt, including all tests that use this logic. | In J1699-5
| 3-1047 | Update the wording in Test 6.1 that requests a two trip DTC. | In J1699-5
| 3-1048 | INF $F877 should not have a phase in period. | In J1699-5
| 3-1049 | On partially compliant J2534 Interfaces, errors are logged when attempting to clear filters on a channel that was never opened. | In J1699-5
| 3-1051 | In Test 11.2, do not display IUMPR info for ECUs that do not support IUMPR but do support I/M Readiness. | In J1699-5
| 3-1052 | In Test 11.2, displays IUMPR incorrect initial counters for ECUs that are not on the 'first page'. | In J1699-5
| 3-1053 | Application is locking up at splash screen with Windows 11 Pro, Ver 22H2 OSbuild 22621.1702. | In J1699-5
| 3-1054 | Correct EOBD Code Clear to allow a mixed response only on Key On Engine Running. | In J1699-5
| 3-1057 | Test 11.2, ESC key not functioning correctly, it causes test to FAIL instead of EXIT. | In J1699-5
| 3-1060 | Fix bug that would cause crash if current and previous vehicle test type did not match. | In J1699-5
| 5-10002 | Test 5.8 communication seems to stop after protocol check (no further response received). | In J1699-5
| 5-10003 | Test 5.5, 5.6 FAILs ECUs because physical requests are being made to ECUs that indicate they do not support the parameter. | In J1699-5
| 5-10004 | Support the MIL Exclusion file, like J1699-3 does. | In J1699-5
| 5-10006 | Remove Tester Present option. | In J1699-5
| 5-10007 | Allow subtest to continue after failure in DID-Support DID check. | In J1699-5
Early Nov., 2023
| 3-1062 | SID $09 INF $78 should only apply to diesel MD, MDDC, and HD. | In J1699-5
| 3-1063 | Test 5.17 for SID $09 INF $77 should WARN for 2022-2023 and FAIL for 2024, but currently FAILs. | In J1699-5
| 3-1065 | False fail for unsupported signals in tracking INFs like $17 in EU. | In J1699-5
| 5-10008 | Test 5.8 ends when there is no response to PID $F40D on 29-bit, but a link monitor shows there was a response. | In J1699-5
| 5-10009 | When testing on a light duty car, J1699-5 requires heavy duty PIDs to be present. | In J1699-5
| 5-10010 | Test 5.10 evaluation of PID $F501 issues with engine running. | In J1699-5
| 5-10011 | Test 5.11 of J1699-5, FreezeFrame data shall be requested a SERVICE $19 SUBSERVICE $04. The SW actually requests SERVICE $19 SUBSERVICE $03 instead. | In J1699-5 | NEED DOC
| 5-10012 | Byte #4 in a Freeze Frame Response should be $FF, but J1699-5 expects $04. Test 5.14 / Test 8.3 / Test 9.3 with a false WARNING. Test 6.3 ends up in an infinite loop, based upon the same issue. | In J1699-5
| 5-10014 | Test 5.6 is failing all ECUs if they do not support EGS, CV, EGR, CSER. | In J1699-5 | NEED DOC
| 5-10015 | Change Europe and China compliance types to better match document. | In J1699-5
| 5-10016 | Add definitions for EnergyType and FuelType and remove EngineType and gbDiesel to match document. | In J1699-5
mid-April, 2024
| 3-1066 | Using J1699_CONFIG.INI, Test 5.17 is producing "FAILURE: INF $6 (CVN) supported by less than the expected number of ECUs ( 1 support, 1 expected)!" | In J1699-5
| 3-1067 | Test 5.17, Failure: ECU 18DAF110 INF $42 IEFC-A must return a value of greater than 1. | In J1699-5 | NEED DOC
| 3-1069 | Test 5.17.85, Evaluation criteria is changing to != 0 | In J1699-5 | NEED DOC
| 3-1070 | Test 5.17, INFs $48, $49, and $50 apply to PHEV only. | In J1699-5 | NEED DOC
| 3-1071 | Test 5.17, INF $51 applies to S/S only. | In J1699-5 | NEED DOC
| 3-1072 | Test 5.17, INFs $52-$5B should change from a FAILURE to a WARNING. | In J1699-5 | NEED DOC
| 3-1075 | SID $09 INF $47 should only apply to PHEV/EV. | In J1699-5 | NEED DOC
| 3-1076 | SID $01 PID $A3 has evaluation criteria in code, but there is no requirement in the document. | In J1699-5
| 3-1077 | Q03 Prompt needs to accept >2025 MY. | In J1699-5 | NEED DOC
| 3-1078 | Q10 Prompt needs to accept more than one digit. | In J1699-5
| 3-1079 | Test 5.17 and Test 9.24 must also check INFs $16-$29 are checked for max. value or "not available". | In J1699-5 | NEED DOC
| 3-1080 | Test 5.17 fails with "Supports INF $7A (Must not support INF higher than $78)". Need to support more INFs. | In J1699-5 | NEED DOC
| 5-10005 | Implement J1699-5 specified Dynamic Test (IUMPR equivalent). | In J1699-5
| 5-10017 | PID Supported PIDs F4E0 and F5E0 should both have bit 0 set to 0. | In J1699-5
| 5-10019 | Don't fail vehicles that do not support cylinders 9-16 and do not support SID $22 $F503 and $F505. | In J1699-5 | NEED DOC
| 5-10023 | Add size checks for PID $F4A7,A8,AA,AC-B1,C3,C7,C9,CB,CF,D3,D7. | In J1699-5
| 5-10024 | Clean up defunct, commented-out code and change Physically/Functionally addressed coding for new standard. | In J1699-5
| 5-10025 | Comment out MID tests (and VerifyVehicleState tests when the rest of the test section is not performed). | In J1699-5
| 5-10026 | Fix the misspelling in RequestGrouPIDSupportData to RequestGroupPIDSupportData (found while working on 5-10017). | In J1699-5
| 5-10027 | Fix MDDC check for PID $F4A2 (was incorrectly compared to gstUserInput.eComplianceType, now compared to gstUserInput.eVehicleType). | In J1699-5
| 5-10028 | Fix PID display for $F505 (it used to mistakely show $F504). | In J1699-5
| 5-10029 | Fix formatting of printing of values in PID $F4C9 and $F4CB. | In J1699-5
| 5-10030 | Added function to evaluate INF $F82A. | In J1699-5
| 5-10031 | Added required support evaluate for INF $F883 and $F884. | In J1699-5
| 5-10032 | Added evaluation for PIDs $F4CF,D3,and D7. | In J1699-5
| 5-10033 | Change INF $F817 evaluation to warn if Recent and Lifetime DT values are zero OR equal, warn if Recent and Lifetime FC values are zero for HEV or PHEV, fail if Recent and Lifetime FC values are equal for CONV and S/S, and fail if Fuel Consumed Bytes not supported for EOBD. | In J1699-5
| 5-10034 | Change INF $F818 evaluation to fail if Recent and Lifetime values are equal or zero for CONV and S/S or warn for HEV and PHEV. | In J1699-5
| 5-10035 | Change INF $F819 evaluation to fail if Recent and Lifetime values are equal or zero for Total and Idle PSA and warn if Recent and Lifetime values are zero or Equal for City PSA. | In J1699-5
| 5-10036 | Change INF $F81A-1C evaluation to warn if Recent and Lifetime values are equal or zero for PHEV. | In J1699-5
| 5-10037 | Change INF $F81D-1F,21-2A evaluation to warn if Recent and Lifetime values are equal or zero and warn if it is supported but all timers are "not available". | In J1699-5
| 5-10038 | Change INF $F841 verification to fail if ERT and EOE Active counters are zero for CONV and S/S or warn if P/HEV, and warn if DT and FC Active counter are zero. | In J1699-5
| 5-10039 | Change INF $F842 verification to fail if Idle Active counters (except Idle FC, see 3-1067) are zero and warn if Engine FC, Idle FC, Urban Speed Run, and PKE counters are zero. | In J1699-5
| 5-10040 | Change INF $F845 verification to fail if ERT and EOE lifetime counters are zero for CONV and S/S or warn if P/HEV, and warn if DT and FC lifetime counter are zero. | In J1699-5
| 5-10041 | Change INF $F846 verification to fail if Idle run time lifetime counter are zero and warn if Engine FC and Idle FC, PKE, and Urban Speed Run counters are zero. | In J1699-5
| 5-10042 | Change INF $F847 verification to fail if Total and Idle PSA time Lifetime counters are zero for P/HEV and warn if Urban PSA Active and Lifetime counters are zero for P/HEV. | In J1699-5
| 5-10043 | Change INF $F848-50 verification to fail if Stored and Lifetime counters are zero for PHEV and warn if Active and Lifetime counters are both zero for PHEV. | In J1699-5
| 5-10044 | Change INF $F851-5B verification to fail if Stored and Lifetime counters are zero. | In J1699-5
| 5-10045 | Change INF $F861-66 verification to fail if Active data is not zero after clear codes command. | In J1699-5
| 5-10046 | Change INF $F867-6C verification to fail if Stored data is zero. | In J1699-5
| 5-10047 | Change INF $F86D-76 verification to fail if Lifetime data is zero. | In J1699-5
Early May, 2024
| 5-10001 | Add support for ETHERNET_NDIS |  | IN PROCESS
Late May, 2024
| 3-1007 | Test 5.14 WARNs on SID $96 MID $81 if limits not 0, but this test in in KOER so the limits may not be 0. | J1699-5 Needs This | NEED DOC
| 3-1014 | Support for CNG engines in J1699. | J1699-5 Needs This | NEED DOC
| 3-1046 | Define a new test for a group PID requests containing a known unsupported PID. | J1699-5 Needs This | NEED DOC
| 3-1050 | There is a large time gap between request and receive. | J1699-5 Needs This | NOT ABLE TO DUPLICATE
| 3-1056 | Test 5.9, Not all ECUs respond to SID $04, but no error is flagged. | J1699-5 Needs This | NEED DOC
| 5-10018 | Test 5.5 / Test 5.13 F6xx Validation; Check for supporting what you say you support and verify response size… no test result validation. |  | NEED DOC
| 5-10021 | Support SMAD (INF $92-$93) in Mfg. Specific Drive Cycle.
| 5-10022 | Add ZEV Validation Tests. |  | NEED DOC
Later
| 5-10020 | Allow NRC $22 (Conditions Not Correct) for SID $22 under EOBD. |  | NEED DOC

## J1699-5 Software History
Validated by OEMs | Date Recommended to CARB | Document Version | Software Version | Software Date | J2534 API Version | Initial Model Year Targeted | Comments on Software
NO |  | 3.5 | 03.05.00 | 2024-04-25 | 0404 | 2023 | Fixed Using J1699_CONFIG.INI; Test 5.17 issues; SID $09 INF $47; SID $01 PID $A3; Q03 Prompt needs to accept >2025 MY; Q10 Prompt needs to accept more than one digit; INFs $16-$29 are checked for max. value or "not available"; Implement J1699-5 specified Dynamic Test (IUMPR equivalent); PID Supported PIDs F4E0 and F5E0 should both have bit 0 set to 0; SID $22 $F503 and $F505; Add size checks for PID $F4A7,A8,AA,AC-B1,C3,C7,C9,CB,CF,D3,D7; Comment out MID tests; Added/changed a bunch of INF $F8xx items.
NO |  | 2.6 | 02.06.01 | 2023-11-08 | 0404 | 2023 | Removed Test 5.11 of J1699-5, FreezeFrame data shall be requested a SERVICE $19 SUBSERVICE $04. The SW actually requests SERVICE $19 SUBSERVICE $03 instead; Changed Europe and China compliance types to better match document; Added definitions for EnergyType and FuelType and remove EngineType and gbDiesel to match document; Fixed SID $09 INF $78 should only apply to diesel MD, MDDC, and HD; Fixed Test 5.17 for SID $09 INF $77 should WARN for 2022-2023 and FAIL for 2024, but currently FAILs; Fixed false fail for unsupported signals in tracking INFs like $17 in EU; Fixed Test 5.8 ends when there is no response to PID $F40D on 29-bit, but a link monitor shows there was a response; Fixed When testing on a light duty car, J1699-5 requires heavy duty PIDs to be present; Fixed Test 5.10 evaluation of PID $F501 issues with engine running; Fixed Byte #4 in a Freeze Frame Response should be $FF, but J1699-5 expects $04. Test 5.14 / Test 8.3 / Test 9.3 with a false WARNING; Fixed Test 5.6 is failing all ECUs if they do not support EGS, CV, EGR, CSER.
NO |  | 2.6 | 02.06.00 | 2023-08-07 | 0404 | 2023
NO |  | 2.3 | 02.03.00 | 2023-03-14 | 0404 | 2023 | Test 5.17 GHG INF requirements apply to all HD Vehicles. Should also consider the type of Regulatory/Engine/Powertrain; China6 does not require all or nothing when clearing codes like OBD II does (e.g., during KOER); Test 5.18 incorrectly flags the response to a SID $01 PID $E0, $C0 group request as a failure if $E0 is not supported; In the Dynamic Test, after logging the meta information, it starts somewhere within Test 10.3... So, Tests 10.1 and 10.2 are missing completely, the same is true for the first part of Test 10.3; False failure in Test 5.17 for missing INF $78. This should be for HD and MD only, not LD; Extra space added between "*" and "T" (+000000ms RESULTS: **** Test 5.1 PASSED ****), which breaks tools. It needs to be added back; Test 11.2 with implausible data for initial IUMPR; Test 9.19 and 11.2 crash with China6 selected; Test 11.2 waiting for Bank2 to complete, when vehicle only has Bank1; Clarify wording in Q03 to indicate it is VIN Model Year; Clarify wording in the phase-in WARNING for new INFs; Test 5.6, PID $A1 has an incorret data transformation; Fix display resolution loss in calculation of PID $85 and $96; Change TEST 11.2 on-screen text from RESERVED to GPF for gasoline vehicles; Protocol determination uses SID $01 PID $00, but it should use SID $22 PID $F810.
NO |  | 1.4 | 1.00.00 Beta | 2022-04-15 | 0404 | 2023 | Port of J1699-3 V17.01.00 to UDS.

## Software Change Process
1 | When making changes to the software, strictly follow the requirements in the SAE J1699-3 document.
2 | Do not alter the tests or evaluation criteria defined in the J1699-3 document based on requests from OEMs, suppliers, or other interested parties. In these cases, flag the request and bring it to the attention of Task Force. The software shall only be changed if the J1699-3 document also changes.
3 | In cases where the J1699-3 document is alleged to be inconsistent with the regulations, flag the issue and bring it to the attention of Task Force. Do not attempt to interpret the regulations and do not act independently to alter the software. The software shall only be changed if the J1699-3 document also changes.
4 | Document software changes (whether they are driven by a document change or a bug fix) in SourceForge. All new SourceForge issues shall be discussed during the Software Update portion of each SAE J1699-3 Task Force meeting. Include this information as attachments to the meeting minutes so that it can be distributed to all Task Force members. Work to insure that all known deviations and software bugs are documented in SourceForge.

## Software Version Number
The software version number has the following format: aa.bb.cc[.dd] where aa is the major version number of the J1699-3 document where the implemented requirements are drawn from. bb is the minor version number of the J1699-3 document where the implemented requirements are drawn from. cc is the software update level for the associated aa.bb branch (bug fixes when there has been no change the document where the implemented requirements are drawn from). dd is only used for Beta Test releases (that is, un-official versions), this number started at 0 and increments by one until the official release at which time it is to be removed. The '.dd' is just present to differentiate the Beta Test versions from the 'official' version.